## ELCo
Category | Steps | Description | Person in Charge | Action | Status | Timeline
R&D | step 1 | acquire emoji as images | Mingyang |  | Done
R&D | step 2 | research / ideate a json schema to store image info | Mingyang |  | Done
R&D | step 3 | convert images to structured json | Jason / Mingyang | build a simple pipeline | Done
R&D | step 4 | human review / curate the json result | Jason | validate/correct the json result | Pending
R&D | step 5.1 | fine-tune model based on json result dataset (fine-tuning v1) | Yucheng |  | Done
R&D | Step 5.2 | run benchmark (vision/etc.) model | Yucheng | run a benchmark model to get the baseline result | Done
R&D | Step 6.1 | fine-tune model based on ELCo dataset (fine-tuning v2) | Tianyi |  | Done
R&D | step 6.2 | test and compare model performance | Tianyi |  | Done
R&D | Step 7.1 | research visual LM encoding impact on model performance | Mingyang |  | Optional
R&D | Step 7.2 | extract ELCo emoji images from ELCo dataset | Mingyang |  | Optional
R&D | Step 8 | run task on latest reasoning models (deepseek-R1, gemma 3, gpt-o1-mini etc.) | TBD |  | Optional
Report | step 9.1 | draft poster | All
Report | step 9.2 | finalize poster | All

## Objective
Objective | Description | Status | Conclusion
R1 | (emoji-> image -> detailed description-> embedding), can the process improve EmoTE accuracy? | Done | Improvement, especially on the semantic list, but overall small improvement.
R2 | Compare [5 dimension: visual, posture, color etc. vs 1 dimension: comprehensive_description ] impact on the EmoTE task accuracy | Ongoing
R3 | Fine-tuning (v1 + v2) vs (v1) vs (v2) impact on the EmoTE accuracy | Done | sequence v1 and v2 doesn't impact result much.
R4 | Comparison between visual encoding (vLM) as embedding vs text encoding impact on EmoTe accuracy | Deprecated
R5 | Compare the EmoTE task accuracy on latest reasoning models (deepseek-R1, gemma 3, gpt-o1-[mini] etc.) | Ongoing
Action S/N | Description | PIC
R2 | re-run fine-tuning v1 on [5 dimension vs 1 dimension], check impact | Yucheng
R3 | re-run fine-tuning v1 becoz the result is overwritten and not saved. | Yucheng
R3 | re-run fine-tuning v2 and v1+v2 to get the best result instead of epoch=10. v1 saw the best result at epoch ~=5 | Tianyi
R1 | identify the negative samples to check how we can improve further. [metaphorical, reduplication] | Yucheng / Tianyi
R5 | run the EmoTE task with gpt-o1 model and see the performance. Use the original ELCo dataset | Jason
Admin_1 | draft a poster | Mingyang
EmoTE_Model_[1¦2¦3¦4]
v1 | desciption --> embedding --> fine-tuning
v1+v2
v2+v1